## Construction Plan
Construction Plan
Instructions The table below shows sample construction activities and timeline for a general community solar garden project. Insert or delete rows, if needed, to complete a construction plan of your community solar project. Fill in the corresponding number of weeks you anticipate each activity to take in the columns to the right.
Phase | Construction Activities | start DD/MM/YY | finish DD/MM/YY | # weeks | Construction Time Frame (Weeks)
[5 empty] | Year 1 | [25 empty] | Year 2
[5 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94 | 96 | 98 | 100 | 102 | 104
0. Preparation | Read Program Guide, attend webinars |  |  | 4 | bar: Year 1 2 to Year 1 4
| Begin discussions about the project with local decision makers |  |  | 4 | bar: Year 1 4 to Year 1 6
| Create high level project plan |  |  | 1 | bar: Year 1 4
| Hire project management consultant |  |  | 4 | bar: Year 1 4 to Year 1 6
1. Feasibility Studies and Engagement | Submit Distribution Generator Interconnection Request form to NSPI |  |  | 8 to 24 | bar: Year 1 6 to Year 1 28
| Complete site selection study |  |  | 8 | bar: Year 1 6 to Year 1 12
| Complete preliminary engineering and geotechnical studies |  |  | 8 to 12
| Begin community consultation and engagement |  |  | 4 to 48 | bar: Year 1 6 to Year 2 56
2. Program application | Create Project Budget |  |  | 4 | bar: Year 1 18 to Year 1 20
| Research permit and approval requirements and apply for applicable permits |  |  | 4 | bar: Year 1 18 to Year 1 20
| Identify environmental impacts and create mitigation plan |  |  | 4 | bar: Year 1 22 to Year 1 24
3. Application Outcome | Complete and submit application package |  |  | 12 | bar: Year 1 18 to Year 1 28
| Receive application outcome (approved or declined). If approved, PPA will be awarded |  |  | 4 to 12 | bar: Year 1 30 to Year 1 38
4. Interconnection Procedures | Continue with Distribution Generator Interconnection Procedures (DGIP)- Distribution System Impact Study (DSIS) Phase |  |  | 12 to 24 | bar: Year 1 40 to Year 2 62
5. Design Phase | Completion of engineering and design |  |  | 4 | bar: Year 1 42 to Year 1 44
| Create procurement strategy |  |  | 4 | bar: Year 1 46 to Year 1 48
| Select solar garden technology |  |  | 4 | bar: Year 1 46 to Year 1 48
6. Construction Phase | Select local contractors |  |  | 4 | bar: Year 1 46 to Year 1 48
| Complete tree clearing and additional geotechnical investigation |  |  | 4 to 24 | bar: Year 2 54 to Year 2 56
| Order materials for distribution upgrades |  |  | 4 to 16 | bar: Year 2 54 to Year 2 56
7. Project Completion | Grid upgrades completed by NSPI |  |  | 4 to 8 | bar: Year 2 62 to Year 2 64
| Commence commercial operation |  |  | 4 | bar: Year 2 70 to Year 2 72
8. Operations and subscriptions | Webpage creation, engage and onboard subscribers |  |  | 8 to 24 | bar: Year 2 62 to Year 2 68

## Financial Planning
Financial Planning Template
Project Name
Project Owner(s)
Date
Instructions
1. Obtain all necessary quotes. You are required to attach several quotes as a part of your application package.
2. Complete Sections 1-6 of the template. Each section will assist you with planning your project costs to forecast a proposed power purchase rate.
3. Do not alter green cells. All subtotals and totals in green calculate automatically.
Section 1: Project Budget
Complete the following template with your actual (if already incurred) or projected costs for each line item for your project.
Each cost will not apply to every project. If a line item does not apply to your project, leave the cost as $0.
Include all relevant taxes in each line item.
If you received funding, include the cost you would have incurred for the line item below. You will identify funding and tax credits in Section 2.
| kWdc | kWac | Provided by your engineer in your resource assessment. You are required to attach a copy of your resource assessment to your application package.
Nameplate Capacity
Projected annual net kWhac delivered to the grid | N/A
Project lifetime (years) | 25
Phase 1: Studies & Preparation
Project site selection | 0
Geotechnical study | 0
Preliminary engineering and design | 0
Community engagement | 0
First Nations engagement | 0
Nova Scotia Power- Preliminary Assessment | 0
Environmental assessment, if required (includes solar glare assessment) | 0
Species at risk study | 0
Other- describe | 0
Other- describe | 0
Other- describe | 0
SUBTOTAL PHASE 1 | 0
Phase 2: Permitting, Design, and Construction | 0
Land acquisition | 0
Land upgrades/site preparation | 0
Municipal and TIR permitting | 0
Final design and engineering | 0
Nova Scotia Power - DSIS | 0
NSPI Interconnection (including grid upgrades) | 0
Legal | 0
PV Modules | 0
Inverters | 0
Foundations | 0
Racking | 0
Piles | 0
Electrical, combiner boxes | 0
Cabling and trenching | 0
Other- describe | 0
Other- describe | 0
Other- describe | 0
Other- describe | 0
Fencing and Security | 0
Installation Costs (including roads, commissioning etc.) | 0
Contingency | 0
SUBTOTAL PHASE 2 | 0
Project management and administration | 0
TOTAL | 0
Section 2: Project Funding
Complete the following table, outlining any funding, grants or tax credits you anticipate or have already received for your community solar project. Provide as much information as possible, and use a separate line for each funding program. You are required to provide confirmation letters of approved or preapproved funding with your application package.
Item description (ie.g. project site selection, labour, materials) | Funding Program (funding program name, tax credit name etc.) | Anticipated/Confirmed/Received | Amount
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Project Funding |  |  | 0
Section 3: Project Financing
Complete the following table. If there is one project owner, or the project is owned is a joint venture, complete the first column only (Owner 1).
| Owner 1 | Owner 2
Type of Ownership (e.g. For profit; not-for-profit)
Percent Ownership
Debt Term (e.g. 10, 15, 20 or 25 years)
Debt Interest (Fixed)
Equity ($) | 0 | 0
Grants/Funding ($) | 0 | 0
Loan ($) | 0 | 0
Total Project Loan | 0
Section 4: Operations and Maintenance
Complete the following table, identifying the annual projected costs for line items that are relevant to your project.
Annual Operating Expenses
NSP Subscription Management & Billing | 0 | auto calculated
Land Lease | 0
On site operations/monitoring/maintenance | 0
Project Owner Administration/Coordination/Subscription Management | 0
Insurance | 0
Substation Maintenance, Internet & Snow Clearing | 0
Municipal Tax (incl. property tax) | 0
Total Annual Operations and Maintenance | 0
Section 5: Proposed Power Purchase Rate
1. Considering sections 1-4, and working with your accountant and tax lawyer, complete the table below, providing your proposed power purchase rate for your project.
2. If awarded, your power purchase rate will be the only source of revenue for your project. Your proposed power purchase rate should consider, but is not limited to, the following: funding, grants and tax credits received or planned to receive; all projected expenses such as loan payments, depreciation, operations and maintenance, a decommissiong reserve, and applicable taxes; minimizing or avoiding any cost pressure on rate payers.
3. You are expected to prepare a detailed project budget and forecast with your accountant. The Financial Planning Template is for high level information regarding your program for the purposes of your application, and does not serve as a robost financial planning tool to project your PPA rate.
4. Attach additional information to support your proposed PPA rate.
Proposed power purchase rate ($ per kWh) | 0
Projected net annual energy production (in kWhac) delivered to the grid | 0 | This will be autocalculated based on the information you provide above (C18)
Projected net-income for the life of the project | 0
Projected Return on Equity | 0%
Projected Internal Rate of Return | 0%
Projected annual net-income returned to subscribers/communities | 0
Section 6: Consultant and Accountant
Have you consulted with a tax lawyer to ensure you have properly accounted for the Investment Tax Credit in your financial projections?
Have you consulted with an accountant for your project financials?

## Risk Assessment
Risk Assessment Template
Start Here: Follow Steps 1 - 3 to complete the risk assessment template. For Step 3, populate the "Risk Assessment Table" below. Do not alter colored cells (Risk Score Table and Risk Severity Score) as it auto populates data.
Step 1: Project information
Project Name
Project Owner(s)
Completed by |  | DO NOT ALTER RISK SCORE TABLE Outcomes populate automatically.
Step 2: Use the following table to complete your risk assessment
Probability 1 - 5 | Impact 1 - 5 |  | Risk Score |  | Count
1 Rare | 1 Insignificant |  | 1 to 5 | NEGLIGIBLE | 0
2 Unlikely | 2 Minor |  | 6 to 10 | MINOR | 0
3 Possible | 3 Moderate |  | 11 to 15 | MODERATE | 0
4 Likely | 4 Major |  | 16 to 20 | HIGH | 0
5 Almost Certain | 5 Severe |  | 21 to 25 | CRITICAL | 0
Step 3: Risk Assessment Table
List project risks you identify in the table below under each relevant category. Assess the likelihood and impact level of each risk and your mitigation plan. Do not alter coloured cells. |  | DO NOT ALTER RISK SEVERITY SCORE CELLS
Category | Risk Factor / Description | Likelihood | Impact | Risk Severity Score | Preventative and Protective Measures
Example: Environment | Infrastructure damage due to weather and natural disasters (flooding, hurricanes, wildfire etc) | 3 | 5 | 15 | Conduct environmental studies, have contingency plans for adverse weather and natural events, have proper insurance etc.
Project Site
0
0
0
0
0
Financial
0
0
0
0
0
Legal
0
0
0
0
0
Procurement and Construction
0
0
0
0
0
Community Support and Engagement
0
0
0
0
0
Environmental Impact
Please speak to negative environmental effects that may result from construction or installation activities at the project site and planned mitigation measures.
0
0
0
0
0
Other
0
0
0
0
0